## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DANGIA PIPED WATER SUPPLY SCHEME | SM/15896 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 209/NKWSMD | 10/05/2023 |  | Resource Division | 2.98 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DANGIA PIPED WATER SUPPLY SCHEME | SM/15896 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  |  | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 |  | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DANGIA PIPED WATER SUPPLY SCHEME | SM/15896 | New | WATER SUPPLY SCHEME FOR DANGIA PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000033/2023-2024 | 183/NKWSMD | 04/05/2023 | 30/12/2023 | HARI PRASAD CHETTRI | 480.88 | 106.49 | 22.15 | 50
4 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DANGIA PIPED WATER SUPPLY SCHEME | SM/15896 | New | Material Requisition To Resource Division |  |  | RTOR000130/2023-2024 | 163/NKWSMD | 30/01/2024 |  | Resource Division | 0.22 | 0 | 0 | 0
5 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DANGIA PIPED WATER SUPPLY SCHEME | SM/15896 | New | (CONTINUATION) ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.01.2024 TO 30.04.2024. | Assistant Engineer II | Junior Engineer I | ORD/000258/2023-2024 | 1576/NKWSMD | 29/12/2023 | 27/04/2024 | QRT SECURITY AND MANPOWER SERVICE | 0.79 | 0.6 | 76 | 100
6 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DANGIA PIPED WATER SUPPLY SCHEME | SM/15896 | New | Providing Functional Household Tap Connection under Jal Jeevan Mission for Balance Household at upper Kolbong in connection with Dangia under Darjeeling Division, P.H.E-G.T.A. |  |  | ORD/000246/2023-2024 | 164/NKWSMD | 30/01/2024 | 29/04/2024 | TULSI NIROLA | 23.65 | 0 | 0 | 100
Total | [13 empty] | 516.93 | 107.09 | 20.72