## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME | SM/15897 | New | Water Supply Scheme for Pubong Khasmahal Piped Water Supply Scheme In Rangli Rangliot Block Under Darjeeling District. |  |  | ORD/000056/2023-2024 | 411/NKWSMD | 05/06/2023 | 25/08/2024 | RAMESH AGARWAL | 513.34 | 483.89 | 94.26 | 100
2 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME | SM/15897 | New | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 445/NKWSMD | 07/06/2023 | 07/06/2023 | Resource Division | 3.46 | 0 | 0 | 0
3 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME | SM/15897 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  |  | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 23/08/2023 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
4 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME | SM/15897 | New | Additional work for Water supply Pubong Khasmahal Piped Water Supply Scheme Block Rangli-Rangliot District: Darjeeling. |  |  | ORD/000003/2024-2025 | 967/NKWSMD | 14/06/2024 | 13/08/2024 | RAMESH AGARWAL | 14.12 | 13.27 | 93.98 | 95
5 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME | SM/15897 | New | Gravity Based Water Supply Scheme For Pubong Thulokhola under JAL JEEWAN MISSION under RR Block, District- Darjeeling Detail - (SW No. : SW/140500/2023) |  |  | BILL/00394/2024-2025 | BP-2024-25-285 | 25/09/2024 | 25/09/2024 | DIVISIONAL FOREST OFFICER | 4.35 | 0 | 0 | 0
Total | [13 empty] | 543.68 | 497.16 | 91.44