## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Up & Lr SUMBUK PIPED WATER SUPPLY SCHEME. | SM/15909 | New | Water Supply Scheme For Upper & Lower Sumbuk Piped Water Supply Scheme in Pulbazar Block Under Darjeeling District. |  |  | ORD/000059/2023-2024 | 418/NKWSMD | 05/06/2023 | 30/05/2024 | HARI PRASAD CHETTRI | 278.38 | 219.32 | 78.78 | 100
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Up & Lr SUMBUK PIPED WATER SUPPLY SCHEME. | SM/15909 | New | Material Requisition To Resource Division |  |  | RTOR000049/2023-2024 | 444/NKWSMD | 07/06/2023 | 07/06/2023 | Resource Division | 0.74 | 0 | 0 | 0
Total | [13 empty] | 279.12 | 219.32 | 78.58