## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | BLOOMFIELD TEA GARDEN PWSS | SM/15910 | New | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 812/NKWSMD | 24/07/2023 | 24/07/2023 | Resource Division | 3.42 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | BLOOMFIELD TEA GARDEN PWSS | SM/15910 | New | (Continuation) Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.09.2024 to 31.10.2024. | Assistant Engineer II | Junior Engineer I | ORD/000104/2024-2025 | 1550/NKWSMD | 30/08/2024 | 30/10/2024 | YAMA CONSTRUCTIONS LLP | 0.39 | 0 | 0 | 100
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | BLOOMFIELD TEA GARDEN PWSS | SM/15910 | New | WATER SUPPLY SCHEME FOR BLOOMFIELD PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000097/2023-2024 | 720/NKWSMD | 18/07/2023 | 08/01/2025 | HARI PRASAD CHETTRI | 369.22 | 0 | 0 | 100
4 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | BLOOMFIELD TEA GARDEN PWSS | SM/15910 | New | Additional work of Piped Water Supply Scheme for Bloomfield Tea Garden Piped Water Supply Scheme in Pulbazar Block under Darjeeling District. |  |  | ORD/000002/2024-2025 | 966/NKWSMD | 14/06/2024 | 29/12/2024 | HARI PRASAD CHETTRI | 59.7 | 0 | 0 | 100
Total | [13 empty] | 432.73 | 0 | 0