## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | RIMBICK Piped Water Supply Scheme | SM/16123 | New | WATER SUPPLY SCHEME FOR RIMBICK PIPED WATER SUPPLY SCHEME IN DARJEELING-PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000082/2023-2024 | 681/NKWSMD | 12/07/2023 | 09/12/2026 | NIMA SHERPA | 699.58 | 400.79 | 57.29 | 90
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | RIMBICK Piped Water Supply Scheme | SM/16123 | New | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 757/NKWSMD | 19/07/2023 | 19/07/2023 | Resource Division | 2.77 | 0 | 0 | 0
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | RIMBICK Piped Water Supply Scheme | SM/16123 | New | Additional work for Piped water supply scheme for Rimbick & Namla under Darjeeling Pulbazar Block, Darjeeling Division, PHED, G.T.A. |  |  | ORD/000247/2023-2024 | 87/NKWSMD | 11/01/2024 | 10/04/2024 | NIMA SHERPA | 27.05 | 25.53 | 94.37 | 100
Total | [13 empty] | 729.4 | 426.32 | 58.45