## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | CHEGRA KHASMAHAL Piped Water Supply Scheme | SM/16141 | New | WATER SUPPLY SCHEME FOR CHEGRA KHASMAHAL PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000034/2023-2024 | 184/NKWSMD | 04/05/2023 | 25/10/2024 | GREEN VALLEY CONSTRUCTION | 323.03 | 249.81 | 77.33 | 50
2 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | CHEGRA KHASMAHAL Piped Water Supply Scheme | SM/16141 | New | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 202/NKWSMD | 10/05/2023 | 10/05/2023 | Resource Division | 1.46 | 0 | 0 | 0
3 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | CHEGRA KHASMAHAL Piped Water Supply Scheme | SM/16141 | New | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES UNDER KALIMPONG DISTRICT UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION P.H.E DIRECTORATE, KALIMPONG FROM 01/07/2024 TO 30/09/2024 (3 MONTHS). | Assistant Engineer I | Junior Engineer III | ORD/000012/2024-2025 | 978/NKWSMD | 18/06/2024 | 18/09/2024 | NIM TSHERING LEPCHA | 6.36 | 0 | 0 | 100
4 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | CHEGRA KHASMAHAL Piped Water Supply Scheme | SM/16141 | New | (CONTINUATION) ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.09.2024 TO 31.10.2024. | Assistant Engineer II | Junior Engineer I | ORD/000103/2024-2025 | 1537/NKWSMD | 30/08/2024 | 30/10/2024 | QRT SECURITY AND MANPOWER SERVICE | 0.39 | 0.39 | 100 | 80
Total | [13 empty] | 331.25 | 250.2 | 75.53