## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PANTHABARI FOREST Piped Water Supply Scheme | SM/16143 | New | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 58/NKWSMD | 24/04/2023 | 24/04/2023 | Resource Division | 0.83 | 0 | 0 | 0
2 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PANTHABARI FOREST Piped Water Supply Scheme | SM/16143 | New | WATER SUPPLY SCHEME FOR PANTHABARI PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000001/2023-2024 | 32/NKWSMD | 17/04/2023 | 16/07/2023 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 91.41 | 0 | 0 | 100
3 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PANTHABARI FOREST Piped Water Supply Scheme | SM/16143 | New | Quotation of WBSEDCL for electrical service connection |  |  | BILL/00614/2023-2024 | BP-2023-24-412 | 12/01/2024 | 12/01/2024 | WBSEDCL | 0.82 | 0 | 0 | 0
4 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PANTHABARI FOREST Piped Water Supply Scheme | SM/16143 | New | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES UNDER KALIMPONG DISTRICT UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION P.H.E DIRECTORATE, KALIMPONG FROM 01/01/2025 TO 31/03/2025 (3 MONTHS). | Assistant Engineer I | Junior Engineer III | ORD/000164/2024-2025 | 2411/NKWSMD | 31/12/2024 | 31/03/2025 | NIM TSHERING LEPCHA | 1.45 | 0 | 0 | 0
5 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PANTHABARI FOREST Piped Water Supply Scheme | SM/16143 | New | ADDITIONAL BALANCE WORK ITEMS IN VARIOUS ONGOING PIPED WATER SUPPLY SCHEMES (NIPANIA, BARA CHENGA, PANTHABARI, GARIDHURA & SIMULBARI) UNDER KURSEONG DIVISION, PHED-GTA. |  |  | ORD/000130/2024-2025 | 2228/NKWSMD | 09/12/2024 | 04/12/2025 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 210.35 | 0 | 0 | 10
Total | [13 empty] | 304.85 | 0 | 0