## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PANTHABARI FOREST Piped Water Supply Scheme | SM/16143 | New | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 58/NKWSMD | 24/04/2023 |  | Resource Division | 0.83 | 0 | 0 | 0
2 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PANTHABARI FOREST Piped Water Supply Scheme | SM/16143 | New | Quotation of WBSEDCL for electrical service connection |  |  | BILL/00614/2023-2024 | BP-2023-24-412 | 12/01/2024 |  | WBSEDCL | 0.82 | 0 | 0 | 0
3 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PANTHABARI FOREST Piped Water Supply Scheme | SM/16143 | New | Quotation of WBSEDCL for electrical service connection |  |  | BILL/00614/2023-2024 | BP-2023-24-412 | 12/01/2024 |  | WBSEDCL | 0.82 | 0 | 0 | 0
4 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PANTHABARI FOREST Piped Water Supply Scheme | SM/16143 | New | WATER SUPPLY SCHEME FOR PANTHABARI PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000001/2023-2024 | 32/NKWSMD | 17/04/2023 | 16/07/2023 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 91.41 | 12.11 | 13.25 | 100
Total | [13 empty] | 93.87 | 12.11 | 12.9