## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PANIGHATA Piped Water Supply Scheme | SM/16144 | New | WATER SUPPLY SCHEME FOR PANIGHATA PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000014/2023-2024 | 110/NKWSMD | 28/04/2023 | 14/10/2025 | YAMA CONSTRUCTIONS LLP | 282.78 | 97.7 | 34.55 | 85
2 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PANIGHATA Piped Water Supply Scheme | SM/16144 | New | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 156/NKWSMD | 03/05/2023 | 03/05/2023 | Resource Division | 7.53 | 0 | 0 | 0
3 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PANIGHATA Piped Water Supply Scheme | SM/16144 | New | Material Requisition To Resource Division |  |  | RTOR000119/2023-2024 | 1188/NKWSMD | 06/10/2023 | 06/10/2023 | Resource Division | 7.53 | 0 | 0 | 0
4 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PANIGHATA Piped Water Supply Scheme | SM/16144 | New | payment for wbsedcl |  |  | BILL/00709/2023-2024 | BP-2023-24-478 | 28/01/2024 | 28/01/2024 | WBSEDCL | 6.1 | 0 | 0 | 0
5 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PANIGHATA Piped Water Supply Scheme | SM/16144 | New | payment for wbsedcl |  |  | BILL/00708/2023-2024 | BP-2023-24-477 | 28/01/2024 | 28/01/2024 | WBSEDCL | 4.54 | 0 | 0 | 0
6 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PANIGHATA Piped Water Supply Scheme | SM/16144 | New | ADDITIONAL WORK FOR PANIGHATA PIPED WATER SUPPLY SCHEME UNDER BLOCK- KURSEONG DISTRICT DARJEELING, KURSEONG DIVISION PHED-GTA. |  |  | ORD/000171/2024-2025 | 161/NKWSMD | 04/02/2025 | 10/01/2026 | S S CONSTRUCTIONS | 52.49 | 0 | 0 | 80
Total | [13 empty] | 360.95 | 97.7 | 27.07