## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR SIMRING TEA GARDEN IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/16145 | New | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 764/NKWSMD | 19/07/2023 | 19/07/2023 | Resource Division | 1.84 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR SIMRING TEA GARDEN IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/16145 | New | WATER SUPPLY SCHEME FOR SIMRING TEA GARDEN PIPED WATER SUPPLY SCHEME IN BLOCK KURSEONG UNDER DISTRICT DARJEELING. |  |  | ORD/000084/2023-2024 | 683/NKWSMD | 12/07/2023 | 04/09/2024 | M/S S S CONSTRUCTION | 417.8 | 367.43 | 87.94 | 50
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR SIMRING TEA GARDEN IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/16145 | New | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR SIMRING TEA GARDEN IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000055/2025-2026 | 820/NKWSMD | 09/06/2025 | 08/08/2025 | M/S S S CONSTRUCTION | 14.61 | 0 | 0 | 0
Total | [13 empty] | 434.26 | 367.43 | 84.61