## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | TUKDAH FOREST PIPED WATER SUPPLY SCHEME | SM/16157 | New | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 244/NKWSMD | 12/05/2023 | 12/05/2023 | Resource Division | 0.77 | 0 | 0 | 0
2 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | TUKDAH FOREST PIPED WATER SUPPLY SCHEME | SM/16157 | New | TAKDAH FOREST WATER SUPPLY SCHEME UNDER JAL JEEWAN MISSION |  |  | BILL/00388/2024-2025 | BP-2024-25-283 | 24/09/2024 | 24/09/2024 | DIVISIONAL FOREST OFFICER | 7 | 0 | 0 | 0
3 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | TUKDAH FOREST PIPED WATER SUPPLY SCHEME | SM/16157 | New | WATER SUPPLY SCHEME FOR TUKDAH FOREST PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000030/2023-2024 | 108/NKWSMD | 28/04/2023 | 04/01/2027 | RAMESH AGARWAL | 108.34 | 0 | 0 | 95
Total | [13 empty] | 116.11 | 0 | 0