## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | LR BANSBOTAY & LR LINGSAY BONG PIPED WATER SUPPLY SCHEME | SM/16159 | New | Water Supply Scheme For Lower Bansbotay & Lower Lingsay Bong Piped Water Supply Scheme in Pulbazar Block Under Darjeeling District. |  |  | ORD/000057/2023-2024 | 415/NKWSMD | 05/06/2023 | 02/12/2023 | HARI PRASAD CHETTRI | 287.97 | 134.57 | 46.73 | 80
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | LR BANSBOTAY & LR LINGSAY BONG PIPED WATER SUPPLY SCHEME | SM/16159 | New | Material Requisition To Resource Division |  |  | RTOR000048/2023-2024 | 443/NKWSMD | 07/06/2023 | 07/06/2023 | Resource Division | 0.38 | 0 | 0 | 0
Total | [13 empty] | 288.35 | 134.57 | 46.67