## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | RISHIHAT KHASMAHAL PIPED WATER SUPPLY SCHEME | SM/16160 | New | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 210/NKWSMD | 10/05/2023 | 10/05/2023 | Resource Division | 1.21 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | RISHIHAT KHASMAHAL PIPED WATER SUPPLY SCHEME | SM/16160 | New | WATER SUPPLY SCHEME FOR RISHIHAT KHASMAHAL PIPED WATER SUPPLY SCHEME IN DARJEELING PHULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000022/2023-2024 | 121/NKWSMD | 28/04/2023 | 24/12/2023 | MS. SURYA I PVT. LTD COMPANY | 196.43 | 93.24 | 47.47 | 70
Total | [13 empty] | 197.63 | 93.24 | 47.18