## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | RISHIHAT TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/16161 | New | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 208/NKWSMD | 10/05/2023 | 10/05/2023 | Resource Division | 2.42 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | RISHIHAT TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/16161 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR RISHIHAT TEA GARDEN PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. (SM/16161) |  |  | ORD/000150/2024-2025 | 2353/NKWSMD | 19/12/2024 | 17/06/2025 | HARI PRASAD CHETTRI | 53.29 | 0 | 0 | 0
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | RISHIHAT TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/16161 | New | WATER SUPPLY SCHEME FOR RISHIHAT TEA GARDEN PIPED WATER SUPPLY SCHEME PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000012/2023-2024 | 101/NKWSMD | 28/04/2023 | 21/01/2026 | HARI PRASAD CHETTRI | 258.75 | 0 | 0 | 70
Total | [13 empty] | 314.46 | 0 | 0