## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | LATPANICHAR PIPED WATER SUPPLY SCHEME | SM/16162 | New | WATER SUPPLY SCHEME FOR LATPANICHAR FOREST PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT |  |  | ORD/000021/2023-2024 | 120/NKWSMD | 28/04/2023 | 19/10/2025 | MS. SURYA I PVT. LTD COMPANY | 239.52 | 69.03 | 28.82 | 80
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | LATPANICHAR PIPED WATER SUPPLY SCHEME | SM/16162 | New | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 203/NKWSMD | 10/05/2023 | 10/05/2023 | Resource Division | 1.03 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | LATPANICHAR PIPED WATER SUPPLY SCHEME | SM/16162 | New | GRAVITY BASED WATER SUPPLY SCHEME FOR LATPANCHAR FOREST, UNDER JAL JEEVAN MISSION |  |  | BILL/00396/2024-2025 | BP-2024-25-281 | 24/09/2024 | 24/09/2024 | DIVISIONAL FOREST OFFICER | 3.3 | 0 | 0 | 0
4 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | LATPANICHAR PIPED WATER SUPPLY SCHEME | SM/16162 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR LATPANCHAR FOREST PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000366/2025-2026 | 736/NKWSMD | 22/05/2025 | 21/07/2025 | SITA SHARMA | 17.15 | 0 | 0 | 0
Total | [13 empty] | 261.01 | 69.03 | 26.45