## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | KARMAT BUSTY PIPED WATER SUPPLY SCHEME. | SM/16238 | New | Material Requisition To Resource Division |  |  | RTOR000062/2023-2024 | 776/NKWSMD | 19/07/2023 | 19/07/2023 | Resource Division | 0.26 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | KARMAT BUSTY PIPED WATER SUPPLY SCHEME. | SM/16238 | New | WATER SUPPLY SCHEME FOR KARMAT BUSTY PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000091/2023-2024 | 712/NKWSMD | 17/07/2023 | 12/05/2024 | SRINIWAS AGARWAL | 128.73 | 89.76 | 69.72 | 100
Total | [13 empty] | 129 | 89.76 | 69.58