## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR JUNGPANA TEA GARDEN,IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/16352 | New | WATER SUPPLY SCHEME FOR JUNGPANA TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000029/2023-2024 | 107/NKWSMD | 28/04/2023 | 23/12/2024 | SRINIWAS AGARWAL | 690.58 | 359.48 | 52.06 | 100
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR JUNGPANA TEA GARDEN,IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/16352 | New | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 247/NKWSMD | 12/05/2023 | 12/05/2023 | Resource Division | 4.4 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR JUNGPANA TEA GARDEN,IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/16352 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. |  |  | BILL/00683/2023-2024 | BP-2023-24-445 | 20/01/2024 | 20/01/2024 | DIVISIONAL FOREST OFFICER | 11.16 | 0 | 0 | 0
Total | [13 empty] | 706.14 | 359.48 | 50.91