## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR NAHORI TEA GARDEN ( BALASOM) (PART) | SM/16386 | New | SURFACE WATER BASED NAHORI TEA GARDEN (BALASOM) (PART) PWSS TO ACCOMODTE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE |  |  | ORD/000339/2022-2023 | 2736/NKWSMD | 03/03/2023 | 02/03/2024 | M/S. ASHOK KUMAR PERIWAL | 659.52 | 403.62 | 61.2 | 100
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR NAHORI TEA GARDEN ( BALASOM) (PART) | SM/16386 | New | Material Requisition To Resource Division |  |  | RTOR000261/2022-2023 | 2772/NKWSMD | 10/03/2023 | 10/03/2023 | Resource Division | 2.03 | 0 | 0 | 0
Total | [13 empty] | 661.54 | 403.62 | 61.01