## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Maharani Tea Garden | SM/16474 | New | Material Requisition To Resource Division |  |  | RTOR000262/2022-2023 | 2773/NKWSMD | 10/03/2023 | 10/03/2023 | Resource Division | 3.01 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Maharani Tea Garden | SM/16474 | New | SURFACE WATER BASED MAHARANI TEA GARDEN PWSS TO ACCOMODTE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE |  |  | ORD/000340/2022-2023 | 2737/NKWSMD | 03/03/2023 | 16/05/2025 | SRINIWAS AGARWAL | 440.47 | 314.56 | 71.41 | 65
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Maharani Tea Garden | SM/16474 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR MAHARANI TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000047/2025-2026 | 636/NKWSMD | 05/05/2025 | 02/09/2025 | SURAJMULL PRABHUDAYAL | 16.26 | 0 | 0 | 100
Total | [13 empty] | 459.74 | 314.56 | 68.42