## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR OKATIY TEA GARDEN PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/16532 | New | WATER SUPPLY SCHEME FOR OKAITY TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000036/2023-2024 | 185/NKWSMD | 04/05/2023 | 25/12/2025 | GREENPRO ENGINEERING | 1588.65 | 837.47 | 52.72 | 90
2 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR OKATIY TEA GARDEN PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/16532 | New | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 248/NKWSMD | 12/05/2023 | 12/05/2023 | Resource Division | 7.85 | 0 | 0 | 0
3 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR OKATIY TEA GARDEN PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/16532 | New | WATER SUPPLY SCHEME FOR OKAITY TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. |  |  | BILL/00216/2024-2025 | BP-2024-25-172 | 01/08/2024 | 01/08/2024 | WBSEDCL | 50.95 | 0 | 0 | 0
4 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR OKATIY TEA GARDEN PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/16532 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR OKAITY TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000230/2025-2026 | 793/NKWSMD | 03/06/2025 | 02/08/2025 | GREENPRO ENGINEERING | 8.79 | 0 | 0 | 0
Total | [13 empty] | 1656.24 | 837.47 | 50.56