## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MAKAI BARI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/16533 | New | WATER SUPPLY SCHEME FOR MAKAIBARI TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000017/2023-2024 | 117/NKWSMD | 28/04/2023 | 21/07/2025 | VINAYAK CONSTRUCTION | 1144.27 | 985.6 | 86.13 | 5
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MAKAI BARI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/16533 | New | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 155/NKWSMD | 03/05/2023 | 03/05/2023 | Resource Division | 4.98 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MAKAI BARI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/16533 | New | ADDITIONAL WORK FOR MAKAIBARI TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK- KURSEONG DISTRICT-DARJEELING KURSEONG DIVISION PHED/GTA |  |  | ORD/000036/2025-2026 | 652/NKWSMD | 05/05/2025 | 03/08/2025 | MAGMA CONSORTIUM | 30.47 | 0 | 0 | 0
Total | [13 empty] | 1179.72 | 985.6 | 83.55