## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR LIZZIEPUR TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/16534 | New | Preparation of Re-draft of proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 03 (three) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer I | Junior Engineer IV | ORD/000274/2023-2024 | 1594/NKWSMD | 29/12/2023 | 08/01/2024 | CIVIL ENGINEERING CONSULTANCY | 0.57 | 0 | 0 | 100
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR LIZZIEPUR TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/16534 | New | AUGMENTATION OF LEFT OUT HABITATION OF CART ROAD GHAYABARI-II G.P. UNDER KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000008/2025-2026 | 494/NKWSMD | 09/04/2025 | 06/10/2025 | SHAKTI CONSTRUCTION | 93.45 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR LIZZIEPUR TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/16534 | New | WATER SUPPLY SCHEME FOR LIZZIPUR TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000229/2023-2024 | 1291/NKWSMD | 17/10/2023 | 16/10/2024 | SHAKTI CONSTRUCTION | 1461.53 | 831.64 | 56.9 | 100
Total | [13 empty] | 1555.56 | 831.64 | 53.46