## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme for Mahanadi tea Garden in Kurseong block under Darjeeling District | SM/16535 | New | WATER SUPPLY SCHEME FOR MAHANADI TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000005/2023-2024 | 92/NKWSMD | 27/04/2023 | 22/12/2024 | VINAYAK CONSTRUCTION | 1041.6 | 686.05 | 65.87 | 100
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme for Mahanadi tea Garden in Kurseong block under Darjeeling District | SM/16535 | New | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 154/NKWSMD | 03/05/2023 | 03/05/2023 | Resource Division | 6.37 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme for Mahanadi tea Garden in Kurseong block under Darjeeling District | SM/16535 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. |  |  | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 01/11/2023 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
Total | [13 empty] | 1097.21 | 686.05 | 62.53