## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR SOURINI BASTY PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT | SM/16627 | New | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 278/NKWSMD | 17/05/2023 | 17/05/2023 | Resource Division | 4.55 | 0 | 0 | 0
2 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR SOURINI BASTY PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT | SM/16627 | New | WATER SUPPLY SCHEME FOR SAURINI BASTI PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000041/2023-2024 | 224/NKWSMD | 10/05/2023 | 05/01/2024 | GARGO TRADERS | 917.05 | 0 | 0 | 80
3 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR SOURINI BASTY PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT | SM/16627 | New | ADDITIONAL WORK FOR SAURINI BUSTY PIPED WATER SUPPLY SCHEME UNDER BLOCK-MIRIK DISTRICT-DARJEELING, KURSEONG DIVISION PHE-GTA. |  |  | ORD/000026/2025-2026 | 594/NKWSMD | 29/04/2025 | 28/07/2025 | ALLIED INSTRUMENTS | 22.62 | 0 | 0 | 0
Total | [13 empty] | 944.22 | 0 | 0