## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR DUPTIN BUSTY,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/16628 | New | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 251/NKWSMD | 12/05/2023 | 12/05/2023 | Resource Division | 3.42 | 0 | 0 | 0
2 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR DUPTIN BUSTY,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/16628 | New | PAYMENT FOR WBSEDCL |  |  | BILL/00855/2023-2024 | BP-2023-24-656 | 23/03/2024 | 23/03/2024 | WBSEDCL | 18.95 | 0 | 0 | 0
3 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR DUPTIN BUSTY,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/16628 | New | WATER SUPPLY SCHEME FOR DUPTIN BUSTY PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000028/2023-2024 | 104/NKWSMD | 28/04/2023 | 25/05/2025 | SHAKTI CONSTRUCTION | 830.5 | 0 | 0 | 100
Total | [13 empty] | 852.87 | 0 | 0