## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | SINGALILA FOREST PWSS | SM/16771 | New | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 151/NKWSMD | 03/05/2023 |  | Resource Division | 0.47 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | SINGALILA FOREST PWSS | SM/16771 | New | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 212/NKWSMD | 10/05/2023 |  | Resource Division | 0.47 | 0 | 0 | 0
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | SINGALILA FOREST PWSS | SM/16771 | New | WATER SUPPLY SCHEME FOR SINGALILA FOREST PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000003/2023-2024 | 87/NKWSMD | 27/04/2023 | 26/04/2024 | NIMA SHERPA | 364.9 | 121.76 | 33.37 | 70
Total | [13 empty] | 365.83 | 121.76 | 33.28