## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | SINGALILA FOREST PWSS | SM/16771 | New | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 151/NKWSMD | 03/05/2023 | 03/05/2023 | Resource Division | 0.47 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | SINGALILA FOREST PWSS | SM/16771 | New | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 212/NKWSMD | 10/05/2023 | 10/05/2023 | Resource Division | 0.47 | 0 | 0 | 0
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | SINGALILA FOREST PWSS | SM/16771 | New | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR SINGALILA UNDER PULL BIJANBARI BLOCK DARJEELING DIVISION PHED TO ACCOMODATE FHTC IN PUL BIJANBARI BLOCK. |  |  | ORD/000158/2024-2025 | 2368/NKWSMD | 20/12/2024 | 20/03/2025 | RINZI SHERPA | 29 | 0 | 0 | 0
4 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | SINGALILA FOREST PWSS | SM/16771 | New | WATER SUPPLY SCHEME FOR SINGALILA FOREST PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000003/2023-2024 | 87/NKWSMD | 27/04/2023 | 01/09/2025 | NIMA SHERPA | 364.9 | 320.91 | 87.95 | 100
Total | [13 empty] | 394.84 | 320.91 | 81.28