## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | BARBATIA KHASMAHAL PWSS | SM/18189 | New | WATER SUPPLY SCHEME FOR BARBATIA KHASMAHAL PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000032/2023-2024 | 182/NKWSMD | 04/05/2023 | 29/03/2024 | MS. SURYA I PVT. LTD COMPANY | 194.76 | 64 | 32.86 | 95
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | BARBATIA KHASMAHAL PWSS | SM/18189 | New | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 211/NKWSMD | 10/05/2023 | 10/05/2023 | Resource Division | 0.77 | 0 | 0 | 0
Total | [13 empty] | 195.53 | 64 | 32.73