## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR AMBOOTIA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/18282 | New | WATER SUPPLY SCHEME FOR AMBOOTIA TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000096/2023-2024 | 719/NKWSMD | 18/07/2023 | 19/05/2026 | SRINIWAS AGARWAL | 1473.72 | 184.77 | 12.54 | 65
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR AMBOOTIA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/18282 | New | Material Requisition To Resource Division |  |  | RTOR000087/2023-2024 | 815/NKWSMD | 24/07/2023 | 24/07/2023 | Resource Division | 7.71 | 0 | 0 | 0
Total | [13 empty] | 1481.43 | 184.77 | 12.47