## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | HUM TUKDAH KHASMAHAL PWSS | SM/18316 | New | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 760/NKWSMD | 19/07/2023 | 19/07/2023 | Resource Division | 9.95 | 0 | 0 | 0
2 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | HUM TUKDAH KHASMAHAL PWSS | SM/18316 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  |  | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 23/08/2023 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
3 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | HUM TUKDAH KHASMAHAL PWSS | SM/18316 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer I | Junior Engineer IV | ORD/000275/2023-2024 | 1595/NKWSMD | 29/12/2023 | 08/01/2024 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 0 | 100
4 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | HUM TUKDAH KHASMAHAL PWSS | SM/18316 | New | WATER SUPPLY SCHEME FOR HUM TUKDAH KHASMAHAL PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000076/2023-2024 | 674/NKWSMD | 12/07/2023 | 08/12/2024 | RAMESH AGARWAL | 1210.81 | 0 | 0 | 100
Total | [13 empty] | 1230.11 | 0 | 0