## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/18317 | New | WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000075/2023-2024 | 671/NKWSMD | 12/07/2023 | 07/04/2025 | YAMA CONSTRUCTIONS LLP | 1111.51 | 978 | 87.99 | 100
2 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/18317 | New | Material Requisition To Resource Division |  |  | RTOR000118/2023-2024 | 1189/NKWSMD | 06/10/2023 | 06/10/2023 | Resource Division | 5.08 | 0 | 0 | 0
3 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/18317 | New | PAYMENT FOR WBSEDCL |  |  | BILL/00819/2023-2024 | BP-2023-24-535 | 26/02/2024 | 26/02/2024 | WBSEDCL | 4.83 | 0 | 0 | 0
4 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/18317 | New | PAYMENT FOR WBSEDCL |  |  | BILL/00818/2023-2024 | BP-2023-24-534 | 26/02/2024 | 26/02/2024 | WBSEDCL | 6.22 | 0 | 0 | 0
5 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/18317 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000170/2024-2025 | 160/NKWSMD | 04/02/2025 | 03/08/2025 | S S CONSTRUCTIONS | 98.42 | 0 | 0 | 100
Total | [13 empty] | 1226.06 | 978 | 79.77