## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | SITTONG KHASMAHAL PWSS | SM/18336 | New | WATER SUPPLY SCHEME FOR SITTONG KHASMAHAL PIPED WATER SUPPLY SCHEME KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000113/2023-2024 | 850/NKWSMD | 27/07/2023 | 11/07/2025 | HIMALAYAN CONSTRUCTION | 921.25 | 504.19 | 54.73 | 85
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | SITTONG KHASMAHAL PWSS | SM/18336 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR SITTONG KHASMAHAL PIPED WATER SUPPLY SCHEME KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000052/2025-2026 | 775/NKWSMD | 28/05/2025 | 24/11/2025 | HIMALAYAN CONSTRUCTION | 122.95 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | SITTONG KHASMAHAL PWSS | SM/18336 | New | Material Requisition To Resource Division |  |  | RTOR000013/2024-2025 | 13/NKWSMD | 06/01/2025 | 06/01/2025 | Resource Division | 3.91 | 0 | 0 | 0
4 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | SITTONG KHASMAHAL PWSS | SM/18336 | New | WATER SUPPLY SCHEME FOR SITTONG KHASMAHAL PIPED WATER SUPPLY SCHEME KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | BILL/00103/2025-2026 |  | 03/07/2025 | 03/07/2025 | DIVISIONAL FOREST OFFICER | 3.45 | 0 | 0 | 0
Total | [13 empty] | 1051.56 | 504.19 | 47.95