## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME ACHHALAL HATTA PWSS IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/18601 | New | WATER SUPPLY SCHEME FOR ACHHALAL HATTA PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000151/2023-2024 | 879/NKWSMD | 03/08/2023 | 02/08/2024 | YAMA CONSTRUCTIONS LLP | 2563.35 | 2464.07 | 96.13 | 50
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME ACHHALAL HATTA PWSS IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/18601 | New | Material Requisition To Resource Division |  |  | RTOR000132/2023-2024 | 174/NKWSMD | 08/02/2024 | 08/02/2024 | Resource Division | 12.22 | 0 | 0 | 0
Total | [13 empty] | 2575.57 | 2464.07 | 95.67