## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN(GAYABARI),IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/18633 | New | PAYMENT FOR WBSEDCL |  |  | BILL/00817/2023-2024 | BP-2023-24-533 | 26/02/2024 | 26/02/2024 | WBSEDCL | 6.18 | 0 | 0 | 0
2 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN(GAYABARI),IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/18633 | New | PAYMENT FOR WBSEDCL |  |  | BILL/00815/2023-2024 | BP-2023-24-531 | 26/02/2024 | 26/02/2024 | WBSEDCL | 6.19 | 0 | 0 | 0
3 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN(GAYABARI),IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/18633 | New | PAYMENT FOR WBSEDCL |  |  | BILL/00816/2023-2024 | BP-2023-24-532 | 26/02/2024 | 26/02/2024 | WBSEDCL | 5.88 | 0 | 0 | 0
4 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN(GAYABARI),IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/18633 | New | WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000155/2023-2024 | 883/NKWSMD | 03/08/2023 | 20/11/2026 | GARGO TRADERS | 1359.83 | 927.88 | 68.24 | 80
5 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN(GAYABARI),IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/18633 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000023/2025-2026 | 591/NKWSMD | 29/04/2025 | 26/10/2025 | ALLIED INSTRUMENTS | 55.54 | 0 | 0 | 90
Total | [13 empty] | 1433.61 | 927.88 | 64.72