## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR SEYOK TEA GARDEN PWSS,IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/18634 | New | Material Requisition To Resource Division |  |  | RTOR000098/2023-2024 | 974/NKWSMD | 21/08/2023 | 21/08/2023 | Resource Division | 6.01 | 0 | 0 | 0
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR SEYOK TEA GARDEN PWSS,IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/18634 | New | WATER SUPPLY SCHEME FOR SEYOK TEA GARDEN PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW-SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. |  |  | BILL/00097/2024-2025 | BP-2024-25-87 | 08/07/2024 | 08/07/2024 | WBSEDCL | 7.65 | 0 | 0 | 0
Total | [13 empty] | 13.66 | 0 | 0