## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY FOR SOURENA TEA ESTATE,IN MIRIK BLOCK UNDER DARJEELING | SM/18635 | New | Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/10/2023 to 31/11/2023. |  | Junior Engineer I | ORD/000206/2023-2024 | 1153/NKWSMD | 29/09/2023 | 29/11/2023 | THE ELECTRIC SPHERE | 0.94 | 0 | 0 | 0
2 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY FOR SOURENA TEA ESTATE,IN MIRIK BLOCK UNDER DARJEELING | SM/18635 | New | PAYMENT FOR WBSEDCL |  |  | BILL/00820/2023-2024 | BP-2023-24-536 | 26/02/2024 | 26/02/2024 | WBSEDCL | 4.38 | 0 | 0 | 0
3 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY FOR SOURENA TEA ESTATE,IN MIRIK BLOCK UNDER DARJEELING | SM/18635 | New | WATER SUPPLY SCHEME FOR SAURENA TEA ESTATE PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000156/2023-2024 | 884/NKWSMD | 03/08/2023 | 02/08/2024 | GARGO TRADERS | 1832.72 | 1162.99 | 63.46 | 75
4 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY FOR SOURENA TEA ESTATE,IN MIRIK BLOCK UNDER DARJEELING | SM/18635 | New | ADDITIONAL WORK FOR SAURENA TEA ESTATE PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK: UNDER DARJEELING DISTRICT.UNDER KURSEONG DIVISION PHED-GTA. |  |  | ORD/000025/2025-2026 | 593/NKWSMD | 29/04/2025 | 26/10/2025 | GARGO TRADERS | 64.04 | 0 | 0 | 0
Total | [13 empty] | 1902.08 | 1162.99 | 61.14