## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-II PWSS | SM/18659 | New | Material Requisition To Resource Division |  |  | RTOR000128/2023-2024 | 52/NKWSMD | 09/01/2024 | 09/01/2024 | Resource Division | 13.36 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-II PWSS | SM/18659 | New | i)Hydrological study of Rungdong Khola River under Water Supply Scheme for Darjeeling Pulbazar Pumping-I ii) Hydrological study of Jamboni River under Water Supply Scheme for Darjeeling Pulbazar Pumping-II iii) Hydrological study of Jhepi Khola River under Water Supply Scheme for Darjeeling Pulbazar Pumping-III iv)Hydrological study of Balason Khola River (locally khown as Rangbhang Khola) under Water Supply Scheme for Mangarjung Tea Garden and other three villages (MVS), Block- Jorebunglow Sukhiapokhari. v) Hydrological study of Rangbhang River (Khola) Pumping water Supply Scheme for Mirik Municipal Town and EN-Route villages District- Darjeeling (under AMRUT) |  |  | BILL/00218/2024-2025 | BP-2024-25-179 | 01/08/2024 | 01/08/2024 | JADAVPUR UNIVERSITY | 17.51 | 0 | 0 | 0
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-II PWSS | SM/18659 | New | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES UNDER KALIMPONG DISTRICT UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION P.H.E DIRECTORATE, KALIMPONG FROM 01/04/2025 TO 30/06/2025 (3 MONTHS). |  |  | ORD/000235/2024-2025 | 414/NKWSMD | 28/03/2025 | 28/06/2025 | NIM TSHERING LEPCHA | 3.61 | 0 | 0 | 0
4 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-II PWSS | SM/18659 | New | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES FROM 5 BLOCKS OF DARJEELING HILLS UNDER SINDHAP SUB DISTRICT LABORATORY UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, KALIMPONG FROM 01/04/2025 TO 30/06/2025 (3 MONTHS). |  |  | ORD/000234/2024-2025 | 413/NKWSMD | 28/03/2025 | 28/06/2025 | NIM TSHERING LEPCHA | 2.17 | 0 | 0 | 0
5 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-II PWSS | SM/18659 | New | Surveying, planning, designing, delivery, erection, construction, commissioning and completion in all respect of all CIVIL, ELECTRICAL and MECHANICAL works like Intake,WTP, Raw Water rising main, Clear Water rising main (CWR at WTP to different GLR sites), GLRs, Chlorine cum switch room, Boundary Wall etc. including all allied related and enabling works for WATER SUPPLY SCHEME FOR DARJEELING PULBAZAR PUMPING - II SPRING WATER SUPPLY SCHEME followed by 03 (three) months of Trial Run and subsequent Operation and maintenance of 03 (Three) years. |  |  | ORD/000169/2024-2025 | 134/NKWSMD | 28/01/2025 | 28/07/2026 | SSN DEVELOPERS | 8170.65 | 0 | 0 | 15
6 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-II PWSS | SM/18659 | New | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 5 (Five) Months for G.T.A Area from 01/02/2025 to 30/06/2025. Note: With effect from the date of issuing work order. | Assistant Engineer II | Junior Engineer II | ORD/000218/2024-2025 | 146/NKWSMD | 31/01/2025 | 30/06/2025 | YAMA CONSTRUCTIONS LLP | 0.83 | 1.98 | 239.71 | 0
7 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-II PWSS | SM/18659 | New | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES FROM 5 BLOCKS OF DARJEELING HILLS UNDER SINDHAP SUB DISTRICT LABORATORY UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, KALIMPONG FROM 01/07/2025 TO 30/09/2025 (3 MONTHS). |  |  | ORD/000113/2025-2026 | 942/NKWSMD | 30/06/2025 | 30/09/2025 | NIM TSHERING LEPCHA | 2.17 | 0 | 0 | 0
8 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-II PWSS | SM/18659 | New | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES UNDER KALIMPONG DISTRICT UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION P.H.E DIRECTORATE, KALIMPONG FROM 01/07/2025 TO 30/09/2025 (3 MONTHS). |  |  | ORD/000114/2025-2026 | 943/NKWSMD | 30/06/2025 | 30/09/2025 | NIM TSHERING LEPCHA | 3.61 | 0 | 0 | 0
Total | [13 empty] | 8213.92 | 1.98 | 0.02