## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | GINGLAM & GIELIE TEA GARDEN PWSS | SM/18721 | New | Material Requisition To Resource Division |  |  | RTOR000103/2023-2024 | 976/NKWSMD | 21/08/2023 | 21/08/2023 | Resource Division | 5.58 | 0 | 0 | 0
2 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | GINGLAM & GIELIE TEA GARDEN PWSS | SM/18721 | New | WATER SUPPLY SCHEME FOR GINGLAM & GIELLE TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000182/2023-2024 | 907/NKWSMD | 11/08/2023 | 29/09/2024 | RAMESH AGARWAL | 1031.49 | 0 | 0 | 100
3 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | GINGLAM & GIELIE TEA GARDEN PWSS | SM/18721 | New | Additional Estimate for Water Supply Scheme for Ginglam & Gielle Tea Garden Piped Water Supply Scheme in Rangli-Rangliot Block under Darjeeling District. (SM/18721) |  |  | ORD/000021/2024-2025 | 985/NKWSMD | 18/06/2024 | 17/08/2024 | RAMESH AGARWAL | 32.15 | 0 | 0 | 100
Total | [13 empty] | 1069.21 | 0 | 0