## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | SAMALBONG PWSS | SM/18722 | New | Material Requisition To Resource Division |  |  | RTOR000100/2023-2024 | 963/NKWSMD | 21/08/2023 | 21/08/2023 | Resource Division | 3.35 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | SAMALBONG PWSS | SM/18722 | New | ADDITIONAL WORK FOR SAMALBONG PIPED WATER SUPPLY SCHEME UNDER BLOCK-PULBAZAR DISTRICT-DARJEELING. |  |  | ORD/000028/2025-2026 | 596/NKWSMD | 29/04/2025 | 26/10/2025 | GARGO TRADERS | 98.47 | 0 | 0 | 0
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | SAMALBONG PWSS | SM/18722 | New | WATER SUPPLY SCHEME FOR SAMALBONG PIPED WATER SUPPLY SCHEME DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000178/2023-2024 | 937/NKWSMD | 16/08/2023 | 12/04/2025 | GARGO TRADERS | 1200.76 | 820.63 | 68.34 | 80
Total | [13 empty] | 1302.58 | 820.63 | 63