## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | TUKDAH, LAPCHU KHASMAHAL & LAPCHU TEA GARDEN PWSS | SM/18724 | New | Material Requisition To Resource Division |  |  | RTOR000099/2023-2024 | 962/NKWSMD | 21/08/2023 | 21/08/2023 | Resource Division | 8.29 | 0 | 0 | 0
2 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | TUKDAH, LAPCHU KHASMAHAL & LAPCHU TEA GARDEN PWSS | SM/18724 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR TUKDAH, LAPCHU KHASMAHAL & LAPCHU TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000148/2024-2025 | 2351/NKWSMD | 19/12/2024 | 17/06/2025 | THUPDEN BHUTIA | 117.43 | 0 | 0 | 0
3 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | TUKDAH, LAPCHU KHASMAHAL & LAPCHU TEA GARDEN PWSS | SM/18724 | New | WATER SUPPLY SCHEME FOR TUKDAH,LAPCHU KHASMAHAL & LAPCHU TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000176/2023-2024 | 935/NKWSMD | 16/08/2023 | 15/08/2024 | THUPDEN BHUTIA | 1654.3 | 586.32 | 35.44 | 80
Total | [13 empty] | 1780.02 | 586.32 | 32.94