## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | BADAMTAM TEA GARDEN PWSS | SM/18725 | New | Material Requisition To Resource Division |  |  | RTOR000104/2023-2024 | 966/NKWSMD | 21/08/2023 | 21/08/2023 | Resource Division | 6.07 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | BADAMTAM TEA GARDEN PWSS | SM/18725 | New | WATER SUPPLY SCHEME FOR BADAMTAM TEA GARDEN PWSS IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000184/2023-2024 | 947/NKWSMD | 17/08/2023 | 09/11/2025 | ASHIRWAD CONSTRUCTION CO. | 1087.52 | 574.76 | 52.85 | 100
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | BADAMTAM TEA GARDEN PWSS | SM/18725 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer I,Assistant Engineer II | Junior Engineer IV | ORD/000270/2023-2024 | 1590/NKWSMD | 29/12/2023 | 08/01/2024 | MANOMITA CIVIL ENGINEERING CONSULTANCY PVT LTD | 0.95 | 0 | 0 | 100
4 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | BADAMTAM TEA GARDEN PWSS | SM/18725 | New | ADDITIONAL WORK FOR BADAMTAM TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK: DARJEELING PULBAZAR DISTRICT DARJEELNG UNDER DARJEELING DIVISION PHED GTA. |  |  | ORD/000054/2025-2026 | 817/NKWSMD | 05/06/2025 | 03/09/2025 | ASHIRWAD CONSTRUCTION CO | 29.04 | 0 | 0 | 0
Total | [13 empty] | 1123.59 | 574.76 | 51.15