## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | LEBONG & MINERAL TEA GARDEN PWSS | SM/18726 | New | Material Requisition To Resource Division |  |  | RTOR000102/2023-2024 | 965/NKWSMD | 21/08/2023 | 21/08/2023 | Resource Division | 7.65 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | LEBONG & MINERAL TEA GARDEN PWSS | SM/18726 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR LEBONG & MINERAL TEA GARDEN PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. (SM/18726) |  |  | ORD/000149/2024-2025 | 2352/NKWSMD | 19/12/2024 | 17/02/2025 | KUNCHAN JUNGA ENTERPRISES | 19.15 | 0 | 0 | 0
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | LEBONG & MINERAL TEA GARDEN PWSS | SM/18726 | New | WATER SUPPLY SCHEME FOR LEBONG & MINERAL TEA GARDEN PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000183/2023-2024 | 946/NKWSMD | 17/08/2023 | 30/12/2025 | KUNCHAN JUNGA ENTERPRISES | 1046.33 | 590.48 | 56.43 | 85
4 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | LEBONG & MINERAL TEA GARDEN PWSS | SM/18726 | New | Additional work for Piped Water Supply Scheme for Lebong & Mineral Tea Garden (SM/18726) under Darjeeling Division, PHED, GTA |  |  | ORD/000020/2024-2025 | 984/NKWSMD | 18/06/2024 | 17/08/2024 | KUNCHAN JUNGA ENTERPRISES | 49.4 | 0 | 0 | 0
Total | [13 empty] | 1122.53 | 590.48 | 52.6