## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | PESHOK TEA GARDEN PWSS | SM/18728 | New | WATER SUPPLY SCHEME FOR PESHOK TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000185/2023-2024 | 949/NKWSMD | 17/08/2023 | 16/08/2026 | VINAYAK CONSTRUCTION | 956.42 | 500.73 | 52.36 | 80
2 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | PESHOK TEA GARDEN PWSS | SM/18728 | New | PROVIDING FHTC UNDER JAL JEEVAN MISSION FOR BALANCE HOUSEHOLD AT 9TH MILE (MAMTA PARK LAMAHATTA) PESHOKE ROAD, LAMAHATTA UNDER DARJEELING DIVISION, P.H.E DEPTT, GTA |  |  | ORD/000175/2023-2024 | 934/NKWSMD | 16/08/2023 | 15/10/2023 | PUSHKAR GURUNG | 13.64 | 12.64 | 92.67 | 100
3 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | PESHOK TEA GARDEN PWSS | SM/18728 | New | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 961/NKWSMD | 21/08/2023 | 21/08/2023 | Resource Division | 6.15 | 0 | 0 | 0
4 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | PESHOK TEA GARDEN PWSS | SM/18728 | New | ADDITIONAL WORK FOR PESHOK TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK-RANGLI RANGLIOT DISTRICT-DARJEELING. |  |  | ORD/000034/2025-2026 | 649/NKWSMD | 05/05/2025 | 01/11/2025 | MAGMA CONSORTIUM | 74.02 | 0 | 0 | 0
Total | [13 empty] | 1050.24 | 513.38 | 48.88