## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | RONGCHONG AND LABDA PWSS | SM/18729 | New | Piped Water Supply Scheme for Rongchong and Labda under Kurseong Division. Scheme code - 18729 TSM/018103 |  |  | BILL/00090/2024-2025 | BP-2024-25-97 | 08/07/2024 | 08/07/2024 | DIVISIONAL FOREST OFFICER | 5.04 | 0 | 0 | 0
2 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | RONGCHONG AND LABDA PWSS | SM/18729 | New | WATER SUPPLY SCHEME FOR RANGCHONG & LABDA PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT |  |  | ORD/000177/2023-2024 | 936/NKWSMD | 16/08/2023 | 12/04/2025 | VINAYAK CONSTRUCTION | 1186.16 | 0 | 0 | 100
3 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | RONGCHONG AND LABDA PWSS | SM/18729 | New | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR RONGCHONG AND LABDA IN RANGLI RANGLIOT BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION. PHED/GTA. |  |  | ORD/000040/2025-2026 | 655/NKWSMD | 05/05/2025 | 01/11/2025 | DAJUBHAI CONSTRUCTION | 107.78 | 0 | 0 | 0
Total | [13 empty] | 1298.98 | 0 | 0