## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | DAWAIPANI & TUKDAH TEA GARDEN PWSS | SM/18752 | New | Material Requisition To Resource Division |  |  | RTOR000113/2023-2024 | 999/NKWSMD | 24/08/2023 | 24/08/2023 | Resource Division | 8.16 | 0 | 0 | 0
2 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | DAWAIPANI & TUKDAH TEA GARDEN PWSS | SM/18752 | New | ADDITIONAL WORK FOR DAWAIPANI & TUKDAH TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000037/2025-2026 | 650/NKWSMD | 05/05/2025 | 01/11/2025 | VINAYAK CONSTRUCTION | 130.55 | 0 | 0 | 0
Total | [13 empty] | 138.71 | 0 | 0