## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-III PWSS | SM/18792 | New | Material Requisition To Resource Division |  |  | RTOR000129/2023-2024 | 53/NKWSMD | 09/01/2024 | 09/01/2024 | Resource Division | 9.98 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-III PWSS | SM/18792 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  |  | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 25/10/2024 | KAMAKHAYA CONSTRUCTION | 179.69 | 9.98 | 5.55 | 80
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-III PWSS | SM/18792 | New | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 6 (Six) Months, other than G.T.A Area from 01/08/2024 to 31/01/2025. Note: With effect from the date of issuing work order. | Assistant Engineer II | Junior Engineer I | ORD/000118/2024-2025 | 1349/NKWSMD | 31/07/2024 | 27/01/2025 | SUJIT DEB | 0.99 | 2.2 | 222.55 | 100
4 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-III PWSS | SM/18792 | New | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 5 (Five) Months, other than G.T.A Area from 01/02/2025 to 30/06/2025. Note: With effect from the date of issuing work order. | Assistant Engineer II | Junior Engineer I | ORD/000219/2024-2025 | 147/NKWSMD | 31/01/2025 | 30/06/2025 | SUJIT DEB | 0.83 | 1.97 | 238.46 | 0
Total | [13 empty] | 191.48 | 14.15 | 7.39