## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-III PWSS | SM/18792 | New | Material Requisition To Resource Division |  |  | RTOR000129/2023-2024 | 53/NKWSMD | 09/01/2024 | 09/01/2024 | Resource Division | 9.98 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-III PWSS | SM/18792 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  |  | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 25/10/2024 | KAMAKHAYA CONSTRUCTION | 179.69 | 9.98 | 5.55 | 80
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-III PWSS | SM/18792 | New | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 6 (Six) Months, other than G.T.A Area from 01/08/2024 to 31/01/2025. Note: With effect from the date of issuing work order. | Assistant Engineer II | Junior Engineer I | ORD/000118/2024-2025 | 1349/NKWSMD | 31/07/2024 | 27/01/2025 | SUJIT DEB | 0.99 | 2.2 | 222.55 | 100
4 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-III PWSS | SM/18792 | New | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 5 (Five) Months, other than G.T.A Area from 01/02/2025 to 30/06/2025. Note: With effect from the date of issuing work order. | Assistant Engineer II | Junior Engineer I | ORD/000219/2024-2025 | 147/NKWSMD | 31/01/2025 | 30/06/2025 | SUJIT DEB | 0.83 | 1.97 | 238.46 | 0
5 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-III PWSS | SM/18792 | New | Surveying, planning, designing, delivery, erection, construction, commissioning and completion in all respect of all CIVIL, ELECTRICAL and MECHANICAL works like Intake,WTP, Raw Water rising main, Clear Water rising main (CWR at WTP to different GLR sites),GLRs,Chlorine cum switch room , Boundary Wall etc. including all allied related and enabling works for WATER SUPPLY SCHEME FOR DARJEELING PULBAZAR PUMPING - III SPRING WATER SUPPLY SCHEME followed by 03 (three) months of Trial Run and subsequent Operation and maintenance of 03 (Three) years. |  |  | ORD/000107/2024-2025 | 1653/NKWSMD | 11/09/2024 | 16/11/2026 | YATERI CONSTRUCTIONS,JV OF YAMA CONSTRUCTIONS LLP(LEAD PARTNER),AROGYA ENT & BALAJI CONS. | 6744.68 | 697.2 | 10.34 | 50
6 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-III PWSS | SM/18792 | New | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 5 (Five) Months, other than G.T.A Area from 01/07/2025 to 30/11/2025. Note: With effect from the date of issuing work order. | Assistant Engineer II | Junior Engineer I | ORD/000115/2025-2026 | 936/NKWSMD | 26/06/2025 | 23/11/2025 | SUJIT DEB | 0.83 | 0 | 0 | 0
Total | [13 empty] | 6936.99 | 711.35 | 10.25