## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR KALEJ VALLEY PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | SM/18820 | New | WATER SUPPLY SCHEME FOR KALEJ VALLEY PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000202/2023-2024 | 1100/NKWSMD | 21/09/2023 | 20/09/2024 | VINAYAK CONSTRUCTION | 1970.49 | 1792.2 | 90.95 | 50
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR KALEJ VALLEY PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | SM/18820 | New | Material Requisition To Resource Division |  |  | RTOR000117/2023-2024 | 1174/NKWSMD | 05/10/2023 | 05/10/2023 | Resource Division | 3.2 | 0 | 0 | 0
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR KALEJ VALLEY PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | SM/18820 | New | Continuation Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong for 01.08.2024 to 31.08.2024. | Assistant Engineer II | Junior Engineer I | ORD/000096/2024-2025 | 1346/NKWSMD | 31/07/2024 | 31/08/2024 | YAMA CONSTRUCTIONS LLP | 0.39 | 0 | 0 | 100
4 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR KALEJ VALLEY PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | SM/18820 | New | ADDITIONAL WORK FOR KALEJ VALLEY PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING KURSEONG DIVISION PHED/GTA. |  |  | ORD/000039/2025-2026 | 654/NKWSMD | 05/05/2025 | 01/11/2025 | VINAYAK CONSTRUCTION | 142.77 | 0 | 0 | 0
Total | [13 empty] | 2116.86 | 1792.2 | 84.66