## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVETY BASED WATER SUPPLY SCHEME FOR PUBONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/18821 | New | WATER SUPPLY SCHEME FOR PUBONG PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKHIAPOKHRI UNDER DISTRICT DARJEELING. |  |  | ORD/000234/2023-2024 | 1372/NKWSMD | 22/11/2023 | 19/07/2025 | SHAKTI CONSTRUCTION | 1221.09 | 682.86 | 55.92 | 100
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVETY BASED WATER SUPPLY SCHEME FOR PUBONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/18821 | New | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES FROM 5 BLOCKS OF DARJEELING HILLS UNDER SINDHAP SUB DISTRICT LABORATORY UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, KALIMPONG FROM 01/07/2024 TO 30/09/2024 (3 MONTHS). | Assistant Engineer I | Junior Engineer III | ORD/000013/2024-2025 | 977/NKWSMD | 18/06/2024 | 18/09/2024 | NIM TSHERING LEPCHA | 3.19 | 0 | 0 | 100
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVETY BASED WATER SUPPLY SCHEME FOR PUBONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/18821 | New | ADDITIONAL WORK FOR PUBUNG PIPED WATER SUPPLY SCHEME UNDER BLOCK- JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING |  |  | ORD/000044/2025-2026 | 630/NKWSMD | 05/05/2025 | 03/08/2025 | MAHAKAL ENTERPRISES | 28.61 | 0 | 0 | 95
Total | [13 empty] | 1252.88 | 682.86 | 54.5