## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR DOOTERIA PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | SM/18822 | New | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 1172/NKWSMD | 05/10/2023 | 05/10/2023 | Resource Division | 14.44 | 0 | 0 | 0
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR DOOTERIA PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | SM/18822 | New | Preparation of draft proposal including preparation of maps in KML file , DGPS Map ,SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 02 (two) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer I,Assistant Engineer II | Junior Engineer IV | ORD/000276/2023-2024 | 1596/NKWSMD | 29/12/2023 | 08/01/2024 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 0 | 100
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR DOOTERIA PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | SM/18822 | New | WATER SUPPLY SCHEME FOR DOOTERIA TEA GARDEN PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKIAPOKRI UNDER DISTRICT DARJEELING. |  |  | ORD/000201/2023-2024 | 1099/NKWSMD | 21/09/2023 | 19/12/2024 | VINAYAK CONSTRUCTION | 3433.58 | 2126.23 | 61.92 | 50
4 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR DOOTERIA PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | SM/18822 | New | ADDITIONAL WORK FOR DOOTERIA TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING, KURSEONG DIVISION PHED/GTA. |  |  | ORD/000038/2025-2026 | 653/NKWSMD | 05/05/2025 | 01/11/2025 | VINAYAK CONSTRUCTION | 263.39 | 0 | 0 | 0
Total | [13 empty] | 3712.36 | 2126.23 | 57.27